## Tracking Estimation
Issue # | Summary of task | Estiamte (mins) | Coding Effort (mins) | Non-Coding Effort (mins) | Estimator | Implementors
1 | Upload the NextJS template | 0.5 | 0.1 | 0.1 | Ian | Ian
2 | Implement Landing Page mockup | 4 | 1 | 1 | Ian | Ian
3 | Implement Sign in/Sign up page mockup | 0.5 | 0.1 | 0.1 | Ian | Ian
4 | Implement Standings Page Mockup | 1.5 | 0.5 | 0.25 | David | David
5 | Implement Home Dashboard Page Mockup | 1.5 | 0.5 | 0.3 | Noah | Noah
7 | Implement Mockup match page | 1.5 | 0.5 | 0.25 | Mariah | Mariah
9 | Implement Create Event Page Mockup | 1.5 | 0.5 | 0.25 | Alfred | Alfred
11 | Implement accessibility of create event page through dashboard | 0.25 | 0.1 | 0.1 | Noah | Noah
20 | Add links to mockup pages in navbar | 0.1 | 0.1 | 0 | Ian | Ian
6 | Create Prisma schema model for single elimination format tournament | 4 | 2 | 2 | Ian and Mariah | Ian and Mariah
8 | Implement Prisma schema model for log in and user management | 3 | 1 | 1 | Ian | Ian
12 | Implement events already joined to be added to Home Dashboard page | 3 | 1 | 1 | Ian | Ian
24 | Convert dashboard sections into components | 1 | 0.5 | 0.5 | Noah | Noah
25 | Implement mock data with JSON (dashboard) | 0.1 | 0.1 | 0.1 | Noah | Noah
26 | implement match page submission button and verification system | 3 | 2 | 2 | Mariah | Mariah
27 | Add view details button/link to standings page cards | 0.5 | 0.4 | 0.4 | David | David
28 | Replace standings page mock data with Prisma data | 2.5 | 1.5 | 1.5 | David | David
30 | Implement Match Page Backend Integration | 3 | 2 | 2 | Mariah | Mariah
32 | Fix "Events" navbar link to show actual events list instead of Create Event Form | 0.1 | 0.1 | 0.1 | Noah | Noah
33 | Refactor Dashboard Page into Server Wrapper & Client Component | 0.25 | 0.2 | 0.2 | Noah | Noah
34 | Create Mock Dashboard Service Layer | 0.25 | 0.2 | 0.2 | Noah | Noah
35 | Define Strong TypeScript Interfaces for Dashboard Data | 0.25 | 0.2 | 0.2 | Noah | Noah
43 | Issue get rid of standing from match page. | 1 | 1 | 1 | Mariah | Mariah
44 | Remove "My next matches" section from the dashboard | 0.1 | 0.1 | 0.1 | Noah | Noah
50 | Disable Editing When Match Is Verified | 2 | 1 | 1 | Mariah | Mariah
51 | Implement Backend for Event Invites | 2 | 1 | 1 | Ian | Ian
62 | Implement Create Event page functionality | 0.5 | 0.25 | 0.25 | Ian | Ian
48 | Make active events in dashboard functional | 1 | 0.6 | 0.2 | Noah | Noah
49 | Allow standing page and event page to be accessed from the dashboard | 1 | 0.2 | 0 | Noah | Noah
52 | Create routing for unique match pages | 1 | 0.5 | 0.5 | Ian | Ian
53 | Add Back Button on Standings Page to Return to Dashboard | 0.5 | 0.6 | 0.3 | David | David
54 | Implement Standings Details Page | 1.5 | 1 | 0.2 | David | David
60 | Implement Match Status System | 3 | 3.3 | 0.25 | Mariah | Mariah
61 | Fix verification on match page + fix check in | 1 | 0.1 | 1 | Ian, Mariah | Ian, Mariah
64 | Add public/private functionality to schema | 1 | 0.5 | 0.5 | Ian | Ian
65 | Implement front end for invitations and make them functional | 3 | 1.5 | 1.5 | Ian | Ian
66 | Make Landing Page buttons functional | 1 | 0.5 | 0.5 | Alfred | Alfred
67 | Clean up Navbar | 0.6 | 0.5 | 0.05 | Noah | Noah
72 | Implement Player Check-In Flow | 3 | 2.5 | 0.2 | Mariah | Mariah
74 | Add names to users | 0.3 | 0.2 | 0.1 | Ian | Ian
75 | Add join page to navigation | 0.5 | 0.4 | 0.1 | Ian | Ian
76 | Add event/[id] standings to event/tournament page + implement session/userid authentication for standings page | 3 | 2 | 1 | Ian | Ian
78 | Change default page on sign in to dashboard | 0.1 | 0.1 | 0 | Ian | Ian
82 | Fix CI badge | 2 | 1.5 | 0.5 | Ian, Noah | Ian, Noah
83 | Implement dynamic back button | 1 | 0.8 | 0.3 | David | David
85 | Implement features page | 0.5 | 0.4 | 0.1 | Ian | Alfred
86 | Investigate event visibility on public events page | 0.5 | 0.1 | 0.4 | Ian | Ian
88 | Make landing page pull real public events | 1 | 0.8 | 0.3 | David | David
94 | Implement bracket seeding + generation | 4 | 2 | 2 | Ian | Ian
101 | Update invitations to not be single use codes | 1 | 0.5 | 0.5 | Alfred, Ian | Alfred, Ian
103 | Add archived events page | 0.5 | 0.5 | 0.2 | Noah | Noah
104 | Update playwright tests | 2 | 1 | 1 | Ian | Ian
107 | Bring back lower half of landing page | 0.1 | 0.1 | 0 | Ian | Ian
110 | Implement skill based matchmaking | 4 | 3 | 1 | Ian | Ian
111 | Alphabetical sorting for participants list | 0.5 | 0.3 | 0 | David | David
113 | Fix Regenerate Bracket Button on Event Details Page | 0.4 | 0.5 | 0.1 | Mariah, Ian | Mariah,Ian
114 | Add edit functionality to match details page | 1 | 0.5 | 0.5 | Ian | Ian
115 | Add start time to create event page | 0.5 | 0.6 | 0.1 | Noah | Noah
118 | Make events in landing page clickable | 0.5 | 0.3 | 0.1 | Noah | Noah
119 | Update time details in event details | 0.3 | 0.2 | 0.2 | Noah | Noah
122 | Make dashboard card wider | 0.3 | 0.2 | 0.2 | Noah | Noah
123 | Add effect for winner/implement 1st, 2nd, 3rd on event page | 0.5 | 0.4 | 0.15 | Noah | Noah
125 | Add more information to event cards in dashboard | 0.7 | 0.5 | 0.25 | Noah | Noah
130 | Implement event status selector | 0.5 | 0.4 | 0.1 | Ian | Ian
132 | Implement admin pages | 2 | 1.5 | 0.5 | Ian | Ian
137 | Implement teams functionality | 1 | 0.8 | 0.2 | Ian | Ian
141 | Implement double elimination tournaments, fix bracket graphic in event details | 3 | 2.5 | 0.5 | Ian | Ian
124 | Change default event sorting to win/loss | 0.1 | 0.1 | 0 | Ian | Ian
134 | Create playwright tests for admin pages/access/etc | 0.5 | 0.5 | 0 | Ian | Ian
136 | Fix event sort by capacity to prioritize emptier events | 0.1 | 0.1 | 0 | Ian | Ian
139 | Create playwright tests for team based events | 0.5 | 0.5 | 0 | Ian | Ian
147 | Implement full playwright test suite | 0.5 | 0.5 | 0 | Ian | Ian
102 | Implement submit match functionality | 0.5 | 0.5 | 0.2 |  | Noah
23 | Create navigation updates for all new pages | 0.5 | 0.4 | 0.1 |  | Noah

## Summary
Team Member | Software Development Experience (months) | How was coding Effort Tracked | How was non-coding Effort Tracked
Ian | 4 years | Looked at the clock | Also looked at the clock
David | 1 year | Phone timer | Phone timer
Mariah | 20 Months | Phone timer, started and stopped as needed | Phone timer, stopped when finished
Noah | 2 years | Phone timer | Phone timer
Alfred | 4 years | Looked at the clock | Looked at the clock